## Dashboard
PROJECT TASK TRACKER
Multi-Project Development Task Management
| TOTAL PROJECTS |  |  |  | TOTAL TASKS |  |  |  | TASKS COMPLETED
# | Project Name | Total Tasks | Not Started | In Progress | In Review | Done | % Complete | High Priority
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Projects
Project Name | Project Code | Description | Owner | Start Date | Target Date | Status | Priority | Notes
Website Redesign | WEB-001 | Full redesign of company website | Alice Chen | 2026-04-01 | 2026-06-30 | In Progress | High
Mobile App v2 | MOB-002 | Second version of the mobile application | Bob Kim | 2026-04-15 | 2026-08-31 | Planning | High
API Integration | API-003 | Third-party API integrations | Carlos D. | 2026-05-01 | 2026-07-15 | Not Started | Medium

## Tasks
Task ID | Project Name | Task Name | Description | Category | Priority | Status | Assignee | Est. Hours | Actual Hours | Start Date | Due Date | Dependencies | Notes
WEB-001-001 | Website Redesign | UX Wireframes | Create wireframes for all pages | Design | High | Done | Alice Chen | 16 | 16 | 2026-04-01 | 2026-04-07
WEB-001-002 | Website Redesign | UI Design System | Define colors, typography, components | Design | High | In Progress | Alice Chen | 24 | 10 | 2026-04-08 | 2026-04-21 | WEB-001-001
WEB-001-003 | Website Redesign | Homepage Dev | Build homepage with React | Frontend | High | Not Started | David Lee | 20 | 0 | 2026-04-22 | 2026-05-05 | WEB-001-002
MOB-002-001 | Mobile App v2 | Tech Stack Review | Evaluate Flutter vs React Native | Architecture | High | In Progress | Bob Kim | 8 | 4 | 2026-04-15 | 2026-04-20
API-003-001 | API Integration | OAuth 2.0 Setup | Implement OAuth for third-party auth | Backend | Medium | Not Started | Carlos D. | 12 | 0 | 2026-05-01 | 2026-05-10

## How to Use
HOW TO USE THIS TRACKER
1 Add Projects | Go to the Projects sheet. Add each project: name, code, owner, dates, status, and priority.
2 Log Tasks | Go to Tasks. For each task: assign a Task ID (e.g. WEB-001-003), select the Project, fill in name, category, priority, and status.
3 Use Dropdowns | Status, Priority, and Category columns have dropdown menus. Click a cell to see the arrow and pick a value.
4 Track Progress | Update Status as work progresses: Not Started → In Progress → In Review → Done.
5 Dashboard | The Dashboard auto-calculates project totals, completion %, and high-priority task counts. It updates whenever you change data.
6 Task ID Convention | Recommended: [PROJECT-CODE]-[###] e.g. WEB-001-003 (project code + sequential number)
7 Dependencies | In the Dependencies column list the Task IDs that must finish before this task can start.